## Task Timeline
Board - Individual Project Gantt (by weeks)
|  |  | Aug-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020
| Start | End | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
groups - Communication |  |  | 31: groups - Communication
Project Proposal | 31-Aug-2020 | 06-Sep-2020 | 31: Project Proposal (31-Aug-20 - 06-Sep-20); 1: Project Proposal (31-Aug-20 - 06-Sep-20); 2: Project Proposal (31-Aug-20 - 06-Sep-20); 3: Project Proposal (31-Aug-20 - 06-Sep-20); 4: Project Proposal (31-Aug-20 - 06-Sep-20); 5: Project Proposal (31-Aug-20 - 06-Sep-20); 6: Project Proposal (31-Aug-20 - 06-Sep-20)
Requirements Plan | 07-Sep-2020 | 19-Sep-2020 | 7: Requirements Plan (07-Sep-20 - 19-Sep-20); 8: Requirements Plan (07-Sep-20 - 19-Sep-20); 9: Requirements Plan (07-Sep-20 - 19-Sep-20); 10: Requirements Plan (07-Sep-20 - 19-Sep-20); 11: Requirements Plan (07-Sep-20 - 19-Sep-20); 12: Requirements Plan (07-Sep-20 - 19-Sep-20); 13: Requirements Plan (07-Sep-20 - 19-Sep-20); 14: Requirements Plan (07-Sep-20 - 19-Sep-20); 15: Requirements Plan (07-Sep-20 - 19-Sep-20); 16: Requirements Plan (07-Sep-20 - 19-Sep-20); 17: Requirements Plan (07-Sep-20 - 19-Sep-20); 18: Requirements Plan (07-Sep-20 - 19-Sep-20); 19: Requirements Plan (07-Sep-20 - 19-Sep-20)
Initial Requirements Completed | 19-Sep-2020 | 19-Sep-2020 | 19: Initial Requirements Complete (9-Sept-20)
groups - Planning |  |  | 31: groups - Planning
Use Cases | 07-Sep-2020 | 21-Sep-2020 | 7: Use Cases (07-Sep-20 - 21-Sep-20); 8: Use Cases (07-Sep-20 - 21-Sep-20); 9: Use Cases (07-Sep-20 - 21-Sep-20); 10: Use Cases (07-Sep-20 - 21-Sep-20); 11: Use Cases (07-Sep-20 - 21-Sep-20); 12: Use Cases (07-Sep-20 - 21-Sep-20); 13: Use Cases (07-Sep-20 - 21-Sep-20); 14: Use Cases (07-Sep-20 - 21-Sep-20); 15: Use Cases (07-Sep-20 - 21-Sep-20); 16: Use Cases (07-Sep-20 - 21-Sep-20); 17: Use Cases (07-Sep-20 - 21-Sep-20); 18: Use Cases (07-Sep-20 - 21-Sep-20); 19: Use Cases (07-Sep-20 - 21-Sep-20); 20: Use Cases (07-Sep-20 - 21-Sep-20); 21: Use Cases (07-Sep-20 - 21-Sep-20)
WBS | 15-Sep-2020 | 25-Sep-2020 | 15: WBS (15-Sep-20 - 25-Sep-20); 16: WBS (15-Sep-20 - 25-Sep-20); 17: WBS (15-Sep-20 - 25-Sep-20); 18: WBS (15-Sep-20 - 25-Sep-20); 19: WBS (15-Sep-20 - 25-Sep-20); 20: WBS (15-Sep-20 - 25-Sep-20); 21: WBS (15-Sep-20 - 25-Sep-20); 22: WBS (15-Sep-20 - 25-Sep-20); 23: WBS (15-Sep-20 - 25-Sep-20); 24: WBS (15-Sep-20 - 25-Sep-20); 25: WBS (15-Sep-20 - 25-Sep-20)
Tool Selection | 15-Sep-2020 | 25-Sep-2020 | 15: Tool Selection (15-Sep-20 - 25-Sep-20); 16: Tool Selection (15-Sep-20 - 25-Sep-20); 17: Tool Selection (15-Sep-20 - 25-Sep-20); 18: Tool Selection (15-Sep-20 - 25-Sep-20); 19: Tool Selection (15-Sep-20 - 25-Sep-20); 20: Tool Selection (15-Sep-20 - 25-Sep-20); 21: Tool Selection (15-Sep-20 - 25-Sep-20); 22: Tool Selection (15-Sep-20 - 25-Sep-20); 23: Tool Selection (15-Sep-20 - 25-Sep-20); 24: Tool Selection (15-Sep-20 - 25-Sep-20); 25: Tool Selection (15-Sep-20 - 25-Sep-20)
SPMP | 21-Sep-2020 | 02-Oct-2020 | 21: SPMP (21-Sep-20 - 02-Oct-20); 22: SPMP (21-Sep-20 - 02-Oct-20); 23: SPMP (21-Sep-20 - 02-Oct-20); 24: SPMP (21-Sep-20 - 02-Oct-20); 25: SPMP (21-Sep-20 - 02-Oct-20); 26: SPMP (21-Sep-20 - 02-Oct-20); 27: SPMP (21-Sep-20 - 02-Oct-20); 28: SPMP (21-Sep-20 - 02-Oct-20); 29: SPMP (21-Sep-20 - 02-Oct-20); 30: SPMP (21-Sep-20 - 02-Oct-20); 1: SPMP (21-Sep-20 - 02-Oct-20); 2: SPMP (21-Sep-20 - 02-Oct-20)
Gantt Chart | 28-Sep-2020 | 02-Oct-2020 | 28: Gantt Chart (28-Sep-20 - 02-Oct-20); 29: Gantt Chart (28-Sep-20 - 02-Oct-20); 30: Gantt Chart (28-Sep-20 - 02-Oct-20); 1: Gantt Chart (28-Sep-20 - 02-Oct-20); 2: Gantt Chart (28-Sep-20 - 02-Oct-20)
Project Planning Completed | 02-Oct-2020 | 02-Oct-2020 | 2: Project Planning Completed (02-Oct-20)
groups - Model |  |  | 31: groups - Model
Home Page Design | 13-Oct-2020 | 24-Oct-2020 | 13: Home Page Design (13-Oct-20 - 24-Oct-20); 14: Home Page Design (13-Oct-20 - 24-Oct-20); 15: Home Page Design (13-Oct-20 - 24-Oct-20); 16: Home Page Design (13-Oct-20 - 24-Oct-20); 17: Home Page Design (13-Oct-20 - 24-Oct-20); 18: Home Page Design (13-Oct-20 - 24-Oct-20); 19: Home Page Design (13-Oct-20 - 24-Oct-20); 20: Home Page Design (13-Oct-20 - 24-Oct-20); 21: Home Page Design (13-Oct-20 - 24-Oct-20); 22: Home Page Design (13-Oct-20 - 24-Oct-20); 23: Home Page Design (13-Oct-20 - 24-Oct-20); 24: Home Page Design (13-Oct-20 - 24-Oct-20)
Nutrition Page Design | 20-Oct-2020 | 30-Oct-2020 | 20: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 21: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 22: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 23: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 24: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 25: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 26: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 27: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 28: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 29: Nutrition Page Design (20-Oct-20 - 30-Oct-20); 30: Nutrition Page Design (20-Oct-20 - 30-Oct-20)
Home Workout Page Design | 26-Oct-2020 | 06-Nov-2020 | 26: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 27: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 28: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 29: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 30: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 31: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 1: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 2: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 3: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 4: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 5: Home Workout Page Design (26-Oct-20 - 06-Nov-20); 6: Home Workout Page Design (26-Oct-20 - 06-Nov-20)
Gym Workout Page Design | 26-Oct-2020 | 06-Nov-2020 | 26: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 27: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 28: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 29: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 30: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 31: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 1: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 2: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 3: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 4: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 5: Gym Workout Page Design (26-Oct-20 - 06-Nov-20); 6: Gym Workout Page Design (26-Oct-20 - 06-Nov-20)
Website UI Completed | 06-Nov-2020 | 06-Nov-2020 | 6: Website UI Completed (06-Nov-20)
groups - Construction |  |  | 31: groups - Construction
Weight Tracking Implementation | 06-Nov-2020 | 16-Nov-2020 | 6: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 7: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 8: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 9: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 10: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 11: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 12: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 13: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 14: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 15: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20); 16: Weight Tracking Implementation (06-Nov-20 - 16-Nov-20)
User Login Implementation | 06-Nov-2020 | 09-Nov-2020 | 6: User Login Implementation (06-Nov-20 - 09-Nov-20); 7: User Login Implementation (06-Nov-20 - 09-Nov-20); 8: User Login Implementation (06-Nov-20 - 09-Nov-20); 9: User Login Implementation (06-Nov-20 - 09-Nov-20)
Meal Tracking Implementation | 06-Nov-2020 | 16-Nov-2020 | 6: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 7: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 8: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 9: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 10: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 11: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 12: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 13: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 14: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 15: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20); 16: Meal Tracking Implementation (06-Nov-20 - 16-Nov-20)
Home Workout Plan Forum | 09-Nov-2020 | 16-Nov-2020 | 9: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20); 10: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20); 11: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20); 12: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20); 13: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20); 14: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20); 15: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20); 16: Home Workout Plan Forum (09-Nov-20 - 16-Nov-20)
Gym Workout Plan Forum | 09-Nov-2020 | 16-Nov-2020 | 9: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20); 10: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20); 11: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20); 12: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20); 13: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20); 14: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20); 15: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20); 16: Gym Workout Plan Forum (09-Nov-20 - 16-Nov-20)
Calorie Calculator Forum | 09-Nov-2020 | 16-Nov-2020 | 9: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20); 10: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20); 11: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20); 12: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20); 13: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20); 14: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20); 15: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20); 16: Calorie Calculator Forum (09-Nov-20 - 16-Nov-20)
Website Functionality Completed | 16-Nov-2020 | 16-Nov-2020 | 16: Website Functionality Completed (16-Nov-20)
groups - Testing and Deployment |  |  | 31: groups - Testing and Deployment
Testing Plan | 09-Nov-2020 | 20-Nov-2020 | 9: Testing Plan (09-Nov-20 - 20-Nov-20); 10: Testing Plan (09-Nov-20 - 20-Nov-20); 11: Testing Plan (09-Nov-20 - 20-Nov-20); 12: Testing Plan (09-Nov-20 - 20-Nov-20); 13: Testing Plan (09-Nov-20 - 20-Nov-20); 14: Testing Plan (09-Nov-20 - 20-Nov-20); 15: Testing Plan (09-Nov-20 - 20-Nov-20); 16: Testing Plan (09-Nov-20 - 20-Nov-20); 17: Testing Plan (09-Nov-20 - 20-Nov-20); 18: Testing Plan (09-Nov-20 - 20-Nov-20); 19: Testing Plan (09-Nov-20 - 20-Nov-20); 20: Testing Plan (09-Nov-20 - 20-Nov-20)
Deployment Plan | 09-Nov-2020 | 20-Nov-2020 | 9: Deployment Plan (09-Nov-20 - 20-Nov-20); 10: Deployment Plan (09-Nov-20 - 20-Nov-20); 11: Deployment Plan (09-Nov-20 - 20-Nov-20); 12: Deployment Plan (09-Nov-20 - 20-Nov-20); 13: Deployment Plan (09-Nov-20 - 20-Nov-20); 14: Deployment Plan (09-Nov-20 - 20-Nov-20); 15: Deployment Plan (09-Nov-20 - 20-Nov-20); 16: Deployment Plan (09-Nov-20 - 20-Nov-20); 17: Deployment Plan (09-Nov-20 - 20-Nov-20); 18: Deployment Plan (09-Nov-20 - 20-Nov-20); 19: Deployment Plan (09-Nov-20 - 20-Nov-20); 20: Deployment Plan (09-Nov-20 - 20-Nov-20)
Conduct Testing | 20-Nov-2020 | 27-Nov-2020 | 20: Conduct Testing (20-Nov-20 - 27-Nov-20); 21: Conduct Testing (20-Nov-20 - 27-Nov-20); 22: Conduct Testing (20-Nov-20 - 27-Nov-20); 23: Conduct Testing (20-Nov-20 - 27-Nov-20); 24: Conduct Testing (20-Nov-20 - 27-Nov-20); 25: Conduct Testing (20-Nov-20 - 27-Nov-20); 26: Conduct Testing (20-Nov-20 - 27-Nov-20); 27: Conduct Testing (20-Nov-20 - 27-Nov-20)
Website Testing Complete | 27-Nov-2020 | 27-Nov-2020 | 27: Website Testing Complete (27-Nov-20)
Finalized Website ready for Release | 29-Nov-2020 | 29-Nov-2020 | 29: Finalized Website ready for Release (29-Nov-20)
Milestone =