## Expected Milestone Completion
Board - Individual Project Milestone Review (by months)
|  |  | Aug-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Sep-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Oct-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Nov-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Dec-2020 | Jan-2021 | Jan-2021 | Jan-2021 | Jan-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Feb-2021 | Mar-2021 | Mar-2021 | Mar-2021 | Mar-2021 | Mar-2021 | Apr-2021 | Apr-2021 | Apr-2021 | Apr-2021 | May-2021 | May-2021 | May-2021
| Start | End | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17
groups - Communication |  |  | 31: groups - Communication
Initial Requirements Expected Completion | 06-Sep-2020 | 06-Sep-2020 | 14: Initial Requirements Expected Completion (9/6)
Initial Requirements Actual Completion | 19-Sep-2020 | 19-Sep-2020 | 31: Initial Requirements Actual Completion (9/19)
groups - Planning |  |  | 31: groups - Planning
Project Planning Expected Completion | 02-Oct-2020 | 02-Oct-2020 | 28: Project Planning Expected Completion (10/2)
Project Planning Actual Completion | 02-Oct-2020 | 02-Oct-2020 | 28: Project Planning Actual Completion (10/2)
groups - Model |  |  | 31: groups - Model
Website UI Expected Completion | 06-Nov-2020 | 06-Nov-2020 | 2: Website UI Expected Completion (11/6)
Website UI Actual Completion | 15-Nov-2020 | 15-Nov-2020 | 9: Website UI Actual Completion (11/15)
groups - Construction |  |  | 31: groups - Construction
Website Functionality Actual Completion | 09-Nov-2020 | 09-Nov-2020 | 9: Website Functionality Actual Completion (11/9)
Website Functionality Expected Completion | 16-Nov-2020 | 16-Nov-2020 | 16: Website Functionality Expected Completion (11/16)
groups - Testing and Deployment |  |  | 31: groups - Testing and Deployment
Website Testing Actual Completion | 18-Nov-2020 | 18-Nov-2020 | 16: Website Testing Actual Completion (11/18)
Finalized Website ready for Release Actual | 20-Nov-2020 | 20-Nov-2020 | 16: Finalized Website ready for Release Actual Completion (11/20)
Website Testing Expected Completion | 27-Nov-2020 | 27-Nov-2020 | 23: Website Testing Complete Expected Completion (11/27)
Finalized Website ready for Release Expected | 29-Nov-2020 | 29-Nov-2020 | 23: Finalized Website ready for Release Expected Completion (11/29)
Milestone Review:
|  |  | Initial Requirements | The Initial requirements milestone ended up being completed earlier than the originally anticipated deadline. With the project proposal due on September 6th, I had to have brainstormed all initial requirements by this time. Although the requirements were not due until October 2nd, I had planned out the requirements as I began the initial planning of the project in its entirety.
|  |  | Project Planning | As the SPMP, Use Cases, Tools, scheduling, and requirements were all due on October 2nd, I had all of this planning done by the date they were due. The completion of these preparation doctuments allowed my to complete the project planning milestone directly on time. However, I have since made changes to these documents as I had begun to devlop the project and gain a better understanding of more apropriate tools and realistic functionality that would benefit my website and skill level.
|  |  | Website UI | The website UI milestone ended up being completed significantly later than I had originally anticipated. In scheduling and planning the development of my website without prior experience, I envisioned that it would be most beneficial to begin with the visual layout of the site itself, then move on to adding in the functionality of the website. I found in my development process, however, that this was not the case. I instead found it easier to brainstorm a general layout of where different components would go on the site, implementing those components and all website functionality, and finally touching up the UI design once all the components had been put into place. Thus, this milestone ended up being completed after the functionality had been implemented on the site.
|  |  | Website Functionality | As previously mentioned, it was much easier to implement the website functionality prior to designing the UI and visual aspects of the site. For this reason, the website functionality completion milestone ended up being completed sooner than originally anticipated.
|  |  | Website Testing Completion | This milestone also ended up being completed sooner than anticipated. This is primarily because the website needed to be finalized and live before November 29th. In order to reach that deadline on time, I needed to have completed the testing procedure for the website before the 20th and have all website components tested. It was also important to give myself plenty of time to get my site live and properly secured before this final deadline. To leave plenty of time to test every aspect of the site before publishing it, I had to complete the testing by the 18th. I was also able to conduct a significant amount of testing as I was developing the site through the WordPress preview feature.
|  |  | Finalized Website ready for Release | Initially in planning my schedule I had set the milestone deadline for the release and deployment of my finalized website to be November 29th, as this is when the links to our final website are due. However, as I did more research I chose to make my website live slightly sooner in order to allow myself time in case something were to go wrong in this final step. Waiting until the last day to publish my website is very risky, because if something were to go wrong and take more time to publish than expected, I would miss the absolute class deadline. To prevent this, I ensured that the website was finalized and ready for release by November 20th. This gives me an extra 9 days to ensure everything is properly functioning, and the website can finally be deployed on time.